## Abstract
LSS_Bill of Quantities_Renovation of GD (Phase 2)_Draft_01.05.2026
Sr. No. | Item Description | Unit | Quantity | Rate | Amount | Reference
A.Dismantling & Demolishing
A1 | Dismantling of flexible pavement (bituminous courses) by mechanical means and disposal of dismantled material up to a lead of 1 kilometre, as per direction of Engineer-in-charge. | cum |  |  | 0
A2 | Demolishing cement concrete manually/ by mechanical means including disposal of material within 50 metres lead as per direction of Engineer - in - charge. | cum |  |  | 0
A3 | Dismantling tile work in floors and roofs laid in cement mortar including stacking material within 50 metres lead. For thickness of tiles 10 mm to 25 mm | sqm |  |  | 0
A4 | Demolishing R.C.C. work manually/ by mechanical means including stacking of steel bars and disposal of unserviceable material within 50 metres lead as per direction of Engineer - in- charge. | cum |  |  | 0
A5 | Dismantling roofing including ridges, hips, valleys and gutters etc., and stacking the material within 50 metres lead of: G.S. Sheet | sqm |  |  | 0
A6 | Demolishing brick work manually/ by mechanical means including stacking of serviceable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer-in-charge. In cement mortar | cum |  |  | 0
A7 | Dismantling of flushing cistern of all types (C.I./PVC/Vitrious China) including stacking of useful materials near the site and disposal of unserviceable materials within 50 metres lead. | Each |  |  | 0
A8 | Dismantling old plaster or skirting raking out joints and cleaning the surface for plaster including disposal of rubbish to the dumping ground within 50 metres lead. | sqm |  |  | 0
A9 | Dismantling roofing including ridges, hips, valleys and gutters etc., and stacking the material within 50 metres lead of: G.S. Sheet | sqm |  |  | 0
A10 | Careful removal of n false ceiling, including all supporting framework, battens, and fixtures, ensuring minimum damage to adjoining surfaces; stacking of all serviceable material at designated location within site premises as directed by the Engineer-in-Charge. | L.S
| Total A |  |  |  | 0
B. Masonry and Flooring & Wood Work
B1 | Earth work in surface excavation not exceeding 30 cm in depth but exceeding 1.5 m in width as well as 10 sqm on plan including getting out and disposal of excavated earth upto 50 m and lift upto 1.5 m, as directed by Engineer-in- Charge: All kinds of soil | sqm |  |  | 0
B2 | Making plinth protection 50 mm thick of cement concrete 1:3:6 (1 cement : 3 coarse sand (zone-III) derived from natural sources : 6 graded stone aggregate 20 mm nominal size derived from natural sources) over 75 mm thick bed of dry brick ballast 40 mm nominal size, well rammed and consolidated and grouted with fine sand, including necessary excavation, levelling & dressing & finishing the top smooth. | sqm |  |  | 0
B3 | 40 mm thick fine dressed stone flooring over 20 mm (average) thick base of cement mortar 1:5 (1 cement : 5 coarse sand) with joints finished flush. White sand stone | sqm |  |  | 0
B4 | Providing and laying in position cement concrete of specified grade excluding the cost of centering and shuttering - All work up to plinth level : 1:2:4 (1 cement : 2 coarse sand (zone-III) derived from natural sources : 4 graded stone aggregate 20 mm nominal size derived from natural sources) | cum |  |  | 0
B5 | Brick work with common burnt clay F.P.S. (non modular) bricks of class designation 7.5 in foundation and plinth in: Cement mortar 1:4 (1 cement : 4 coarse sand) | cum |  |  | 0
B6 | 12 mm cement plaster finished with a floating coat of neat cement of mix : 1:4 (1 cement: 4 fine sand) | sqm |  |  | 0
B7 | Wall painting with premium acrylic emulsion paint of interior grade, having VOC (Volatile Organic Compound ) content less than 50 grams/ litre of approved brand and manufacture, including applying additional coats wherever required to achieve even shade and colour. Two coats | sqm |  |  | 0
B8 | Structural steel work in single section, fixed with or without connecting plate, including cutting, hoisting, fixing in position and applying a priming coat of approved steel primer all complete. Heavy weight grating made with equal leg angle frame of 40x40x5 and Shutter of 35x35x5 ms angle with Ms flat (30x5)mm at top . the spacing between ms flat is 50mm dimensions, total weight of cover and frame to be not less than 30 kg | kg |  |  | 0
B9 | Providing and laying 4" x 4" Polycrete pavers of dark gray and medium gray shades (as per sample approved) over a prepared base in cement mortar 1:4 (1 part cement : 4 parts coarse sand), including preparation of base, leveling, laying in approved pattern, filling of joints with fine sand/cement slurry, compacting, and curing, complete as per drawing and direction of the Engineer-in-Charge. | sqm |  |  | 0
B10 | Random rubble masonry with hard stone in superstructure above plinth level and upto floor five level, including leveling up with cement concrete 1:6:12 (1 cement : 6 coarse sand : 12 graded stone aggregate 20 mm nominal size) at window sills, ceiling level and the like. Cement mortar 1:6 (1 cement : 6 coarse sand) | cum |  |  | 0
B11 | Steel work in built up tubular (round, square or rectangular hollow tubes etc.) trusses etc., including cutting, hoisting, fixing in position and applying a priming coat of approved steel primer, including welding and bolted with special shaped washers etc. complete. Hot finished seamless type tubes | kg |  |  | 0
B12 | Kota stone slab flooring over 20 mm (average) thick base laid over and jointed with grey cement slurry mixed with pigment to match the shade of the slab, including rubbing and polishing complete with base of cement mortar 1 : 4 (1 cement : 4 coarse sand) : 25 mm thick | sqm |  |  | 0
B13 | Kota stone slabs 20 mm thick in risers of steps, skirting, dado and pillars laid on 12 mm (average) thick cement mortar 1:3 (1 cement: 3 coarse sand) and jointed with grey cement slurry mixed with pigment to match the shade of the slabs, including rubbing and polishing complete. | sqm |  |  | 0
B14 | Providing and laying Ceramic glazed floor tiles of size 300x300 mm(thickness to be specified by the manufacturer) of 1st quality conforming to IS : 15622 of approved make in colours such as White, Ivory, Grey, Fume Red Brown, laid on 20 mm thick cement mortar 1:4 (1 Cement : 4 Coarse sand), Jointing with grey cement slurry @ 3.3 kg/sqm including pointing the joints with white cement and matching pigment etc., complete. | sqm |  |  | 0
B15 | Providing wood work in frames of doors, windows, clerestory windows and other frames, wrought framed and fixed in position with hold fast lugs or with dash fasteners of required dia & length (hold fast lugs or dash fastener shall be paid for separately). Sal wood | cum |  |  | 0
B16 | Providing and fixing panelled or panelled and glazed shutters for doors, windows and clerestory windows, fixing with butt hinges of required size with necessary screws, excluding panelling which will be paid for separately, all complete as per direction of Engineer-in-charge. (Note: Butt hinges and necessary screws shall be paid separately) Second class teak wood | sqm |  |  | 0
B17 | Providing and fixing panelling or panelling and glazing in panelled or panelled and glazed shutters for doors, windows and clerestory windows (Area of opening for panel inserts excluding portion inside grooves or rebates to be measured). Panelling for panelled or panelled and glazed shutters 25 mm to 40 mm thick. |  |  |  | 0
B17.1 | Second class teak wood | sqm |  |  | 0
B17.2 | Float glass panes-4 mm thick glass pane (weight not less than 10 kg/sqm). | sqm |  |  | 0
B18 | Providing and fixing approved quality natural stone cladding of 18–25 mm thickness, in required sizes, shapes, and patterns, on walls, columns, or façade surfaces, as per drawings, specifications, and as directed by the Engineer-in-Charge. | sqm |  |  | 0
B19 | Brick work in plain arches in superstructure above plinth level and upto floor five level including centering and shuttering complete for span up to 6 metres with common burnt clay F.P.S. (non modular) bricks of class designation 7.5 in cement mortar 1:3 (1 cement : 3 coarse sand) | cum |  |  | 0
B20 | Brick work with common burnt clay F.P.S. (non modular) bricks of class designation 7.5 in foundation and plinth in: Cement mortar 1:4 (1 cement : 4 coarse sand) | cum |  |  | 0
B21 | Providing and fixing factory made uPVC door frame made of uPVC extruded sections having an overall dimension as below (tolerance ±1mm), with wall thickness 2.0 mm (± 0.2 mm), corners of the door frame to be Jointed with galvanized brackets and stainless steel screws, joints mitred and Plastic welded. The hinge side vertical of the frames reinforced by galvanized M.S. tube of size 19 X 19 mm and 1 mm (± 0.1 mm) wall thickness and 3 nos. stainless steel hinges fixed to the frame complete as per manufacturer’s specification and direction of Engineerin- charge. Extruded section profile size 48x40 mm | rmt |  |  | 0
B22 | 24 mm thick factory made PVC door shutters made of styles and rails of a uPVC hollow section of size 59x24 mm and wall thickness 2 mm (± 0.2 mm) with inbuilt edging on both sides. The styles and rails mitred and joint at the corners by means of M.S. galvanised/ plastic brackets of size 75x220 mm having wall thickness 1.0 mm and stainless steel screws. The styles of the shutter reinforced by inserting galvanised M.S. tube of size 20x20 mm and 1 mm (± 0.1mm) wall thickness. The lock rail made up of ‘H’ section, a uPVC hollow section of size 100x24 mm and 2 mm (± 0.2 mm) wall thickness, fixed to the shutter styles by means of plastic/galvanised M.S. ‘U’ cleats. The shutter frame filled with a uPVC multi-chambered single panel of size not less than 620 mm, having over all thickness of 20 mm and 1 mm (± 0.1 mm) wall thickness. The panels filled vertically and tie bar at two places by inserting horizontally 6 mm galvanised M.S. rod and fastened with nuts and washers, complete as per manufacturer’s specification and direction of Engineerin- charge. (For W.C. and bathroom door shutter). | sqm |  |  | 0
B23 | Providing & Fixing double skin full height 12 mm thick solid partition of make STYLAM or similar (upto the 7 feet), vertical members to be fixed on the SS plate and caping on the floor. Approved BWR ply as per IS:303, finished both side with approved 1 mm laminate surface complete with door shutter with laminate finish matching to the other available side of the partition, to be incorporated with necessary hinges, sliding bolt from inside, handle and all complete as per design, direction and approval of the Engineer. | sqm |  |  | 0
B24 | Providing and fixing false ceiling at all heights including providing and fixing of frame work made of special sections, power pressed from M.S. sheets and galvanized with zinc coating of 120 gms/sqm (both side inclusive) as per IS : 277 and consisting of angle cleats of size 25 mm wide x 1.6 mm thick with flanges of 27 mm and 37mm, at 1200 mm centre to centre, one flange fixed to the ceiling with dash fastener 12.5 mm dia x 50 mm long with 6 mm dia bolts, other flange of cleat fixed to the angle hangers of 25x10x0.50 mm of required length with nuts & bolts of required size and other end of angle hanger fixed with intermediate G.I. channels 45x15x0.9 mm running at the spacing of 1200 mm centre to centre, to which the ceiling section 0.5 mm thick bottom wedge of 80 mm with tapered flanges of 26 mm each having lips of 10.5 mm, at 450 mm centre to centre, shall be fixed in a direction perpendicular to G.I. intermediate channel with connecting clips made out of 2.64 mm dia x 230 mm long G.I. wire at every junction, including fixing perimeter channels 0.5 mm thick 27 mm high having flanges of 20 mm and 30 mm long, the perimeter of ceiling fixed to wall/partition with the help of rawl plugs at 450 mm centre, with 25 mm long dry wall screws @ 230 mm interval, including fixing of gypsum board to ceiling section and perimeter channel with the help of dry wall screws of size 3.5 x 25 mm at 230 mm c/c, including jointing and finishing to a flush finish of tapered and square edges of the board with recommended jointing compound , jointing tapes , finishing with jointing compound in 3 layers covering upto 150 mm on both sides of joint and two coats of primer suitable for board, all as per manufacturer’s specification and also including the cost of making openings for light fittings, grills, diffusers, cutouts made with frame of perimeter channels suitably fixed, all complete as per drawings, specification and direction of the Engineer in Charge but excluding the cost of painting with :
| Fully Perforated Gypsum Plaster Board of size 1200 x 2400x12.5 mm having approx. 15 % perforated area with perforation size and pattern as approved by the Engineerin- charge and as per manufacturer’s specification, with all 4 sides tapered and backed by acoustical tissue with NRC value not less than 0.60 | sqm |  |  | 0
| Total B |  |  |  | 0
C. Roofing works
C1 | Provide and fixing 19 mm thick marine plywood (water-resistant) onto rafters using suitable screws and washers, including all required fixing materials (nails, screws, washers, adhesives), aligning, leveling, cutting to fit at joints, and finishing. Work to be done complete, as per Engineer‑in‑Charge approval. | sqm |  |  | 0
C2 | Providng and fixing insulated PUFF sheet Roofing with the following specificifications -Panel Specifications: Roof shall be made of sandwich panel, made out of 0.50mm colour coated galvalume steel sheets spec 150gsm & 550mpa as as outer & inner cladding will be 0.40 mm colour coated galvalume sheet sheet spec 150 gsm & 550 mpa on both side of PUFF. Make of the sheet to be OEM TATA/JSW PRIME material. . The total thickness of panel will be 50/80 mm for roof, panel PU foam will be CFC free , self-extinguishing, Fire resistance type having density of 40 kg/cum. The Panel are joined together by tongue & groove method, complete in all respect including all the accessories. Fixing Mechanism: The sheeting will be fixed using galvanized self-drilling, self-tapping fasteners with EPDM seals to ensure secure attachment and weatherproofing. | sqm |  |  | 0
C3 | Providing and fixing flashings, Cappings, valleys manufactured same material as mentioned for roof sheets above in standard lengths of 2.5 mtr. And fixed by means of hex-head self-drilling stitching screws. 501 to 1000 mm Girth in Ridges, flashings, aprons, barge boards (Make of the sheet to be OEM TATA/JSW PRIME material) | rmt |  |  | 0
C4 | Providing and Fixing Gutters manufactured same material as mentioned for roof sheets without PUFF insultation above in standard lengths of 2.5 mtr. And fixed by means of hex-head self-drilling stitching screws. 501 to 1000 mm Girth (Make of the sheet to be OEM TATA/JSW PRIME material) | rmt |  |  | 0
C5 | Providing and fixing precoated galvanised iron profile sheets (size, shape and pitch of corrugation as approved by Engineer-in-Charge) of total coated thickness 0.50 mm (base metal of minimum 0.45 mm thickness with total coating thickness of 0.05mm) with zinc coating 120 grams per sqm as per IS: 277, in 240 mpa steel grade, 5-7 microns epoxy primer onboth side of the sheet and polyester top coat 15-18 microns. Sheet should have protective guard film of 25 microns minimum to avoid scratches during transportation and should be supplied in single length upto 12 metre or as desired by Engineer-in-charge. The sheet shall be fixed using self drilling /self tapping screws of size (5.5x 55 mm) with EPDM seal, complete upto any pitch in horizontal/ vertical or curved surfaces, excluding the cost of purlins, rafters and trusses and including cutting to size and shape wherever required. | sqm |  |  | 0
C6 | Providing and fixing precoated galvanised steel sheet roofing accessories of total coated thickness 0.50 mm (base metal of minimum 0.45 mm thickness with total coating thickness of 0.05 mm) with Zinc coating 120 gram per sqm as per IS: 277, in 240 mpa steel grade, 5-7 microns epoxy primer on both side of the sheet and polyester top coat 15-18 microns using self drilling/ self tapping screws complete : Flashings/ Aprons.( Upto 600 mm) | metre |  |  | 0
C7 | Structural steel work riveted, bolted or welded in built up sections, trusses and framed work, including cutting, hoisting, fixing in position and applying a priming coat of approved steel primer all complete. | kg |  |  | 0
| Total C |  |  |  | 0
D. Plumbing & Sanitary works
D1 | Providing and fixing white vitreous china extended wall mounting water closet of size 780x370x690 mm of approved shape including providing & fixing white vitreous china cistern with dual flush fitting, of flushing capacity 3 litre/ 6 litre (adjustable to 4 litre/ 8 litres), including seat cover, and cistern fittings, nuts, bolts and gasket etc complete. | Each |  |  | 0
D2 | Providing and fixing wash basin with C.I. brackets, 15 mm C.P. brass pillar taps, 32 mm C.P. brass waste of standard pattern, including painting of fittings and brackets, cutting and making good the walls wherever require: White Vitreous China Flat back wash basin size 450x 300 mm with single 15 mm C.P. brass pillar tap | Each |  |  | 0
D3 | Providing and fixing CP Brass 32 mm size Bottle Trap of approved quality & make and as per the direction of Engineer-in-charge. | Each |  |  | 0
D4 | Providing and fixing toilet paper holder : C.P. brass | Each |  |  | 0
D5 | Providing and fixing Health faucet with 1 metre long Flexible tube and C.P. wall hook with PVC & SS Screws wherever required make and as per the direction of Engineer-in-charge. | Each |  |  | 0
D6 | Providing and fixing of C.P. Soap dish complete as per instruction of Engineer-in-charge. | Each |  |  | 0
D7 | Providing and fixing C.P Towel Rail 600mm long fixed to PVC cleats with C.p brass screws including cutting and making good the walls wherever required. | Each |  |  | 0
D8 | Providing and fixing C.P Single lever concealed diverter and Bath spout for bath and shower with Button at Top complete as per direction of the Engineer-in-charge | Each |  |  | 0
D9 | Providing and Fixing Shower Head Over head rose shower with revoling joint ( with boday roation) & 115 mm long shower arm complete as directed by enginner in charge | Each |  |  | 0
D10 | Providing and fixing C.P. brass long body bib cock of approved quality conforming to IS standards and weighing not less than 690 gms.15 mm nominal bore | Each |  |  | 0
D11 | Providing and fixing C.P. brass stop cock (concealed) of standard design and of approved make conforming to IS:8931. 15 mm nominal bore | Each |  |  | 0
D12 | Providing and fixing C.P. brass angle valve for basin mixer and geyser points of approved quality conforming to IS:8931 15 mm nominal bore | Each |  |  | 0
D13 | Providing and fixing of C.P towel ring square/circular fixed to wooden cleats with C.P brass screws including cutting and making good the walls wherever required. | Each |  |  | 0
D14 | Providing and fixing Chlorinated Polyvinyl Chloride (CPVC) pipes, having thermal stability for hot & cold water supply, including all CPVC plain & brass threaded fittings and fixing the pipe with clamps at 1.00 m spacing. This includes jointing of pipes & fittings with one step CPVC solvent cement and the cost of cutting chases and making good the same including testing of joints complete as per direction of Engineer in Charge. Concealed work, including cutting chases and making good the walls etc.
D14.1 | 15 mm nominal dia Pipes | metre |  |  | 0
D14.2 | 20 mm nominal dia Pipes | metre |  |  | 0
D14.3 | 25 mm nominal dia Pipes | metre |  |  | 0
D14.4 | 32 mm nominal dia Pipes | metre |  |  | 0
D15 | Providing and fixing Chlorinated Polyvinyl Chloride (CPVC) pipes, having thermal stability for hot & cold water supply including all CPVC plain & brass threaded fittings This includes jointing of pipes & fittings with one step CPVC solvent cement, trenching, refilling & testing of joints complete as per direction of Engineer in Charge. External work
D15.1 | 15 mm nominal dia Pipes | metre |  |  | 0
D15.2 | 20 mm nominal dia Pipes | metre |  |  | 0
D15.3 | 25 mm nominal dia Pipes | metre |  |  | 0
D15.4 | 32 mm nominal dia Pipes | metre |  |  | 0
D16 | Providing and laying Non Pressure NP-3 class (Medium duty) R.C.C. pipes including collars/spigot jointed with stiff mixture of cement mortar in the proportion of 1:2 (1 cement : 2 fine sand) including testing of jointsetc. Complete 450 mm dia RCC pipes. | rmt |  |  | 0
E17 | Constructing brick masonry manhole in cement mortar 1:4 ( 1 cement : 4 coarse sand ) with R.C.C. top slab with 1:1.5:3 mix (1 cement : 1.5 coarse sand (zone-III) : 3 graded stone aggregate 20 mm nominal size), foundation concrete 1:4:8 mix (1 cement : 4 coarse sand (zone-III) : 8 graded stone aggregate 40 mm nominal size), inside plastering 12 mm thick with cement mortar 1:3 (1 cement : 3 coarse sand) finished with floating coat of neat cement and making channels in cement concrete 1:2:4 (1 cement : 2 coarse sand : 4 graded stone aggregate 20 mm nominal size) finished with a floating coat of neat cement complete as per standard design : Inside size 90x80 cm and 45 cm deep including C.I. cover with frame (light duty) 455x610 mm internal dimensions, total weight of cover and frame to be not less than 38 kg (weight of cover 23 kg and weight of frame 15 kg) : With common burnt clay F.P.S. (non modular) bricks of class designation 7.5 | each |  |  | 0
| Total D |  |  |  | 0
E.Electrical Work
Point Wiring: Point wiring rates are inclusive of 2X2.5 sq mm FRLS PVC insulated stranded copper conductor wires for circuit and 1.5 sq mm FRLS PVC insulated copper conductor insulated earth wire.
E1 | Supply, Wiring, Testing & Commissioning for switch board controlled light points with 3 X 1.5sq.mm FRLS PVC insulated copper wire and earthing with 1.5 sq.mm. FRLS PVC insulated copper wire in insurface / recessed Medium class FRLS PVC conduit, surface tee, saddles,conduit fixing material, MS Connector, including providing & fixing of modular switches as specified complete with modular plate with GI boxes of suitable as complete as required.
E1.1 | First Point (One point controlled by one no. 6 amps switch.) (Normal Light Point) | Nos |  |  | 0
E1.2 | same as the above for Looping Point | Nos |  |  | 0
E2 | Supply, Wiring, Testing & Commissioning for MCB controlled light points with 2 x 2.5 + 1 X 1.5 sq.mm FRLS PVC insulated copper wires in recessed / surface mounted in in insurface / recessed Medium class FRLS PVC conduit, surface tee, saddles, conduit fixing material, MS Connector, along with all required fittings. (Cost of MCB not to be included)
E2.1 | First Point (First light points controlled by one no.6A SP MCB) | Nos |  |  | 0
E2.2 | same as above for the Looping Point | Nos |  |  | 0
E3 | Supply, Wiring, Testing & Commissioning for 6 A multistandard shutterd switched socket outlet with 3 x 1.5 sq mm FRLS PVC insulated copper wire & earthing with 1.5 sq.mm FRLS PVC insulated copper wire in surface / recessed Medium class FRLS PVC conduit, surface tee, saddles,conduit fixing material, MS Connector, including providing & fixing of 6amps modular switch, socket complete with modular plate with suitable size of GI box complete in all respect. | Nos |  |  | 0
E4 | Supply, Wiring, Testing & Commissioning for 1 nos, 16 A shuttered, switched socket outlets with 2 x4 +1 x 2.5 sq.mm FRLS PVC insulated copper wire & earthing with 2.5 sq.mm FRLS PVC insulated copper wire in surface / recessed Medium class FRLS PVC conduit, including providing & fixing of 1 nos. of 16amps modular switched socket outlets alongwith 1nos 16 A switch with modular plate with GI box complete. | Pt. |  |  | 0
E5 | Supply and wiring of exhaust fan point with 3 X 1.5 sq.mm FRLS PVC insulated copper conductor cable in in surface / recessed GI conduit, fixing on surface or wall/ceiling including fixing of saddles etc. including galvanised M.S. box, modular range of plate switches, 6A socket, modular cover plate, PVC insulated copper earth wire etc. complete as required. | Nos |  |  | 0
E6 | Providing and fixing in position the following FRLS PVC conduits including all accessories concealed in F. ceiling (PVC conduit not to be instaUed above false ceilfng) /waif/ floor as required including M.S. junction or pull boxes with 3mm thick perspex sheet cover plate compl-ete with 1.6 mm dia G.I. pull wires in the length of conduit.
E6.1 | 20 mm dia conduit ( 1.6 mm thick) | rmt |  |  | 0
E6.2 | 25 mm dia conduit (1.6 mm thick) | rmt |  |  | 0
E6.3 | 32 mm dia conduit (2.0 mm thick) | rmt |  |  | 0
E7 | Supply,installing ,connecting testing and commissioning of the following double door 1/4 rows vertical type 1.6 mm thick and 1. 4 thick door sheet steel enclosed fully recessed type, TPN Miniature Circuit Breakers Distribution Boards dust proof, verm-in proof, with hinged and lockable doors complete with DP MCB's and inter- connection with copper wire , insulated copper bus bar , cable glands-/conduit entry bushes, bonding to earth and paint-ing. Also provide separate neutral: busbar for each phase. Provide separate ,Earth Links for each phase. Use brass thimbles for connections of all: wires. 1 row for single phase and 4 rows for 3 phase. Provide separate 4 way 63 A main neutral link also. The phase busbar links shall be factory pre insulated.
E7.1 | 10 Way TPN DB, each phase consisting of 8 Nos. 10/20 AMP SP MCB's and controlled by one number 100 mA sensitivity 63 AMPS DP ELCB backed up with 1 no 63 Amps 4 pole MCB. | nos |  |  | 0
E7.2 | 8 Way TPN DB, each phase consisting of 6 Nos. 10/20 AMP SP MCB's and controlled by one number 100 mA sensitivity 63 AMPS DP ELCB backed up with 1 no 63 Amps 4 pole MCB. | nos |  |  | 0
E7.3 | 14 Way TPN DB, each phase consisting of 12 Nos. 10/20 AMP SP MCB's and controlled by one number 100 mA sensitivity 63 AMPS DP ELCB backed up with 1 no 63 Amps 4 pole MCB. | nos |  |  | 0
E8 | Supply & Installation, Testing & Commissioning of 250 mm dia exhaust fan with all accessories as complete as required. (Make -Havells / Oriant / Bajaj ). | Each |  |  | 0
E9 | Supplying of light fixtures as per sample approved. | L.S
| Total E |  |  |  | 0
| Total (A+B+C+D+E) |  |  |  | 0
| Grand Total |  |  |  | 0

## Measurement Sheet
LSS_Take of Sheet_Renovation of GD (Phase 2)_Draft_01.05.2026
S.N0 | Item Description | Nos | L | W | H/D | Qty. | Unit
A.Dismantling & Demolishing
A1 | Dismantling of flexible pavement (bituminous courses) by mechanical means and disposal of dismantled material up to a lead of 1 kilometre, as per direction of Engineer-in-charge.
Outside area as per drawing - 58 sqm
| Taking 100 mm depth |  |  |  |  | 5.8 | cum
| At different location as per structure demand |  |  |  |  | 2.2 | cum
| Total |  |  |  |  | 8 | cum
A2 | Demolishing cement concrete manually/ by mechanical means including disposal of material within 50 metres lead as per direction of Engineer - in - charge.
| Outer Loo |  | 4.959 | 8.609 | 0.1 | 4.2692 | cum
Honoria Court
| Toilet Block | 2 | 6.71 | 10.975 | 0.1 | 14.7285 | cum
| Drying Area | 2 | 1.72 | 2.78 | 0.1 | 0.95632 | cum
| Changing Room | 2 | 2.12 | 4.02 | 0.1 | 1.7045 | cum
| Pantry | 2 | 2.12 | 2.93 | 0.1 | 1.2423 | cum
| Passage | 2 | 2.32 | 1.625 | 1.1 | 8.294 | cum
OGD
| Lower Ground Floor | 1 | 5 | 4.64 | 0.1 | 2.32 | cum
Upper Ground Floor
| Bath | 1 | 3.46 | 2.81 | 0.1 | 0.97226 | cum
| Toilet | 1 | 3.28 | 3.31 | 0.1 | 1.0857 | cum
| Toilet | 1 | 2.61 | 1.485 | 0.1 | 0.38759 | cum
First Floor
| Bath | 1 | 3.46 | 2.81 | 0.1 | 0.97226 | cum
| Toilet | 1 | 3.28 | 3.31 | 0.1 | 1.0857 | cum
| Toilet | 2 | 2.23 | 1.14 | 0.1 | 0.50844 | cum
| At different location as per structure demand |  |  |  |  | 2.37 | cum
| Total |  |  |  |  | 40.8967 | cum
A3 | Dismantling tile work in floors and roofs laid in cement mortar including stacking material within 50 metres lead. For thickness of tiles 10 mm to 25 mm
| Outer Loo |  | 4.959 | 8.609 |  | 42.692 | sqm
Honoria Court
| Toilet Block | 2 | 6.71 | 10.975 | 0.1 | 14.7285 | cum
| Drying Area | 2 | 1.72 | 2.78 | 0.1 | 0.95632 | cum
| Changing Room | 2 | 2.12 | 4.02 | 0.1 | 1.7045 | cum
| Pantry | 2 | 2.12 | 2.93 | 0.1 | 1.2423 | cum
| Passage | 2 | 2.32 | 1.625 | 1.1 | 8.294 | cum
OGD
| Lower Ground Floor | 1 | 5 | 4.64 | 0.1 | 2.32 | cum
Upper Ground Floor
| Bath | 1 | 3.46 | 2.81 | 0.1 | 0.97226 | cum
| Toilet | 1 | 3.28 | 3.31 | 0.1 | 1.0857 | cum
| Toilet | 1 | 2.61 | 1.485 | 0.1 | 0.38759 | cum
First Floor
| Bath | 1 | 3.46 | 2.81 | 0.1 | 0.97226 | cum
| Toilet | 1 | 3.28 | 3.31 | 0.1 | 1.0857 | cum
| Toilet | 2 | 2.23 | 1.14 | 0.1 | 0.50844 | cum
| At different location as per structure demand |  |  |  |  | 3.95 | sqm
| Total |  |  |  |  | 80.8995 | sqm
A4 | Demolishing R.C.C. work manually/ by mechanical means including stacking of steel bars and disposal of unserviceable material within 50 metres lead as per direction of Engineer - in- charge.
| At different location as per structure demand |  |  |  |  | 2 | cum
A5 | Dismantling roofing including ridges, hips, valleys and gutters etc., and stacking the material within 50 metres lead of: G.S. Sheet
| Outer Loo |  |  |  |  | 80.82 | sqm
| At different location as per structure demand |  |  |  |  | 19.18 | sqm
| Total |  |  |  |  | 100 | sqm
A6 | Demolishing brick work manually/ by mechanical means including stacking of serviceable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer-in-charge. In cement mortar
Outer Loo
| 1 | 1 | 8.6 | 0.25 | 2.4 | 5.16 | cum
| 2 | 1 | 5.92 | 0.25 | 2.4 | 3.552 | cum
| 3 | 4 | 1.44 | 0.205 | 2.4 | 2.8339 | cum
| 4 | 5 | 1.45 | 0.22 | 2.4 | 3.828 | cum
Honoria Court
| 1 | 2 | 6.71 | 0.115 | 3.4 | 5.2472 | cum
| 2 | 8 | 1.35 | 0.115 | 3.4 | 4.2228 | cum
| 3 | 8 | 2.98 | 0.115 | 3.4 | 9.3214 | cum
| 4 | 4 | 1.315 | 0.115 | 3.4 | 2.0567 | cum
| 5 | 4 | 1.38 | 0.115 | 3.4 | 2.1583 | cum
| 6 | 4 | 1.36 | 0.115 | 3.4 | 2.127 | cum
| 7 | 2 | 6.67 | 0.115 | 3.4 | 5.2159 | cum
| 8 | 8 | 1.365 | 0.115 | 3.4 | 4.2697 | cum
| 9 | 2 | 4.25 | 0.23 | 3.4 | 6.647 | cum
| 10 | 4 | 1.07 | 0.12 | 3.4 | 1.7462 | cum
OGD
Lower Ground Floor
| Wall 1 | 3 | 1.39 | 0.115 | 3 | 1.4386 | cum
| Wall 2 | 1 | 3.805 | 0.115 | 3 | 1.3127 | cum
| Wall 3 | 4 | 1.23 | 0.115 | 3 | 1.6974 | cum
| Wall 4 | 1 | 5 | 0.115 | 3 | 1.725 | cum
Upper Ground Floor
Bath
| Wall 1 | 2 | 0.979 | 0.115 | 3 | 0.67551 | cum
| Wall 2 | 1 | 1.045 | 0.12 | 3 | 0.3762 | cum
Toilet
| Wall 1 | 3 | 0.97 | 0.115 | 3 | 1.004 | cum
| Wall 2 | 1 | 1.48 | 0.115 | 3 | 0.5106 | cum
| Wall 3 | 1 | 3.51 | 0.115 | 3 | 1.2109 | cum
First Floor
Bath
| Wall 1 | 2 | 0.979 | 0.115 | 3 | 0.67551 | cum
| Wall 2 | 1 | 1.045 | 0.12 | 3 | 0.3762 | cum
Toilet
| Wall 1 | 3 | 0.97 | 0.115 | 3 | 1.004 | cum
| Wall 2 | 1 | 1.48 | 0.115 | 3 | 0.5106 | cum
| Wall 3 | 1 | 3.51 | 0.115 | 3 | 1.2109 | cum
Honoria Court Façade
|  | 7 | 2.85 | 0.23 | 5.55 | 25.4662 | cum
| Total a |  |  |  |  | 97.5807 | cum
Deduction
Honoria Court
| Door 1 | 30 | 0.725 | 0.12 | 2.1 | 5.481 | cum
| Door 2 | 6 | 0.725 | 0.23 | 2.1 | 2.101 | cum
OGD
| Door 1 | 7 | 0.6 | 0.12 | 2.1 | 1.0584 | cum
| Door 2 | 4 | 0.6 | 0.12 | 2.1 | 0.6048 | cum
| Door 3 | 4 | 0.6 | 0.12 | 2.1 | 0.6048 | cum
Honoria Court Façade
| Window 1 | 28 | 0.98 | 0.23 | 1.76 | 11.1077 | cum
| Total b |  |  |  |  | 20.9578 | cum
| Total (a-b) |  |  |  |  | 76.6229 | cum
| At different location as per structure demand |  |  |  |  | 4.17 | cum
| Total |  |  |  |  | 80.7929 | cum
A7 | Dismantling of flushing cistern of all types (C.I./PVC/Vitrious China) including stacking of useful materials near the site and disposal of unserviceable materials within 50 metres lead.
| Outer Loo | 10 |  |  |  | 10
| Honoria Court | 20 |  |  |  | 20
| OGD | 8 |  |  |  | 8
| Total |  |  |  |  | 38
A8 | Dismantling old plaster or skirting raking out joints and cleaning the surface for plaster including disposal of rubbish to the dumping ground within 50 metres lead.
Outer Loo
| Wall 1 |  | 4.96 | 3.01 |  | 58.59 | sqm
| Wall 2 |  | 8.61 | 2.4 |  | 20.664 | sqm
| Wall 3 |  | 4.96 | 3.01 |  | 14.9296 | sqm
| Wall 4 |  | 8.61 | 2.4 |  | 20.664 | sqm
Honoria Court
| Wall 1 | 2 | 6.71 | 3.4 |  | 45.628 | sqm
| Wall 2 | 2 | 10.975 | 3.4 |  | 74.63 | sqm
| Wall 3 | 2 | 6.67 | 3.4 |  | 45.356 | sqm
| Wall 3 | 2 | 6.43 | 3.4 |  | 43.724 | sqm
| Wall 4 | 2 | 3.16 | 3.4 |  | 21.488 | sqm
| Wall 5 | 2 | 3.62 | 3.4 |  | 24.616 | sqm
| Wall 6 | 2 | 2.32 | 3.4 |  | 15.776 | sqm
| Wall 7 | 2 | 2.12 | 3.4 |  | 14.416 | sqm
| Wall 8 | 2 | 4.25 | 3.4 |  | 28.9 | sqm
| Wall 9 | 2 | 2.12 | 3.4 |  | 14.416 | sqm
| Wall 10 | 2 | 2.12 | 3.4 |  | 14.416 | sqm
| Wall 11 | 2 | 6.41 | 3.4 |  | 43.588 | sqm
| Wall 12 | 2 | 0.535 | 3.4 |  | 3.638 | sqm
| Wall 13 | 2 | 1.72 | 3.4 |  | 11.696 | sqm
| Wall 14 | 2 | 1.72 | 3.4 |  | 11.696 | sqm
| Wall 15 | 2 | 2.78 | 3.4 |  | 18.904 | sqm
| Wall 16 | 2 | 2.78 | 3.4 |  | 18.904 | sqm
OGD
Lower Ground Floor
| Wall 1 |  | 5 | 3 |  | 15 | sqm
| Wall 2 |  | 4.6 | 3 |  | 13.8 | sqm
| Wall 3 |  | 5 | 3 |  | 15 | sqm
| Wall 4 |  | 4.6 | 3 |  | 13.8 | sqm
Upper Ground Floor
Bath
| Wall 1 |  | 4.11 | 3 |  | 12.33 | sqm
| Wall 2 |  | 3.305 | 3 |  | 9.915 | sqm
| Wall 3 |  | 0.845 | 3 |  | 2.535 | sqm
| Wall 4 |  | 0.5 | 3 |  | 1.5 | sqm
| Wall 5 |  | 1.74 | 3 |  | 5.22 | sqm
| Wall 6 |  | 3.21 | 3 |  | 9.63 | sqm
Toilet
| Wall 1 |  | 4.105 | 3 |  | 12.315 | sqm
| Wall 2 |  | 3.76 | 3 |  | 11.28 | sqm
| Wall 3 |  | 2.355 | 3 |  | 7.065 | sqm
| Wall 4 |  | 3.305 | 3 |  | 9.915 | sqm
Toilet
| Wall 1 |  | 2.61 | 3 |  | 7.83 | sqm
| Wall 2 |  | 1.48 | 3 |  | 4.44 | sqm
| Wall 3 |  | 2.61 | 3 |  | 7.83 | sqm
| Wall 4 |  | 1.48 | 3 |  | 4.44 | sqm
First Floor
Bath
| Wall 1 |  | 4.11 | 3 |  | 12.33 | sqm
| Wall 2 |  | 3.305 | 3 |  | 9.915 | sqm
| Wall 3 |  | 0.845 | 3 |  | 2.535 | sqm
| Wall 4 |  | 0.5 | 3 |  | 1.5 | sqm
| Wall 5 |  | 1.74 | 3 |  | 5.22 | sqm
| Wall 6 |  | 3.21 | 3 |  | 9.63 | sqm
Toilet
| Wall 1 |  | 4.105 | 3 |  | 12.315 | sqm
| Wall 2 |  | 3.76 | 3 |  | 11.28 | sqm
| Wall 3 |  | 2.355 | 3 |  | 7.065 | sqm
| Wall 4 |  | 3.305 | 3 |  | 9.915 | sqm
Toilet
| Wall 1 | 2 | 2.23 | 3 |  | 13.38 | sqm
| Wall 2 | 2 | 1.14 | 3 |  | 6.84 | sqm
| Wall 3 | 2 | 2.23 | 3 |  | 13.38 | sqm
| Wall 4 | 2 | 1.14 | 3 |  | 6.84 | sqm
| Total a |  |  |  |  | 852.6296 | sqm
Deduction
Outer Loo
| Door 1 | 1 | 0.99 | 1.94 |  | 1.9206 | sqm
| Window 1 | 10 | 0.872 | 0.41 |  | 3.5752 | sqm
| Window 2 | 1 | 0.99 | 1.466 |  | 1.4513 | sqm
Honoria Court
| Door 1 | 2 | 1.28 | 2.65 |  | 6.784 | sqm
| Door 2 | 2 | 0.9 | 2.65 |  | 4.77 | sqm
| Door 3 | 2 | 0.75 | 2.65 |  | 3.975 | sqm
| Window 1 | 16 | 1.2 | 1.05 |  | 20.16 | sqm
| Window 2 | 4 | 1.2 | 1.05 |  | 5.04 | sqm
OGD
| Door 1 | 1 | 1.05 | 2.1 |  | 2.205 | sqm
| Door 2 | 3 | 0.75 | 2.1 |  | 4.725 | sqm
| Door 3 | 4 | 0.75 | 2.1 |  | 6.3 | sqm
| Window 1 | 3 | 0.45 | 1.4 |  | 1.89 | sqm
| Ventilator 1 | 4 | 0.9 | 0.5 |  | 1.8 | sqm
| Ventilator 2 | 6 | 0.9 | 0.8 |  | 4.32 | sqm
| Ventilator 3 | 2 | 0.9 | 0.8 |  | 1.44 | sqm
| Total b |  |  |  |  | 70.3561 | sqm
| Total (a-b) |  |  |  |  | 782.2735 | sqm
| At different location as per structure demand |  |  |  |  | 17.73 | sqm
| Total |  |  |  |  | 800.0035 | sqm
A9 | Dismantling roofing including ridges, hips, valleys and gutters etc., and stacking the material within 50 metres lead of: G.S. Sheet
| For Old GD roof sheet area |  |  |  |  | 420 | sqm
A10 | Careful removal of n false ceiling, including all supporting framework, battens, and fixtures, ensuring minimum damage to adjoining surfaces; stacking of all serviceable material at designated location within site premises as directed by the Engineer-in-Charge.
| At different location as per structure demand |  |  |  |  | 1 | Job
B. Masonry and Flooring & Wood Work
B1 | Earth work in surface excavation not exceeding 30 cm in depth but exceeding 1.5 m in width as well as 10 sqm on plan including getting out and disposal of excavated earth upto 50 m and lift upto 1.5 m, as directed by Engineer-in- Charge: All kinds of soil
Outside area as per drawing
| Outer Loo |  |  |  |  | 28.84 | sqm
| At different location as per structure demand |  |  |  |  | 11.16 | sqm
| Total |  |  |  |  | 40 | sqm
B2 | Making plinth protection 50 mm thick of cement concrete 1:3:6 (1 cement : 3 coarse sand (zone-III) derived from natural sources : 6 graded stone aggregate 20 mm nominal size derived from natural sources) over 75 mm thick bed of dry brick ballast 40 mm nominal size, well rammed and consolidated and grouted with fine sand, including necessary excavation, levelling & dressing & finishing the top smooth.
Outer Loo
| Location 1 |  | 6.907 | 0.55 |  | 3.7989 | sqm
| Location 2 |  | 9.46 | 0.55 |  | 5.203 | sqm
| Location 3 |  | 6.907 | 0.55 |  | 3.7989 | sqm
| Location 4 |  | 9.46 | 0.55 |  | 5.203 | sqm
| At different location as per structure demand |  |  |  |  | 2 | sqm
| Total |  |  |  |  | 20.0037 | sqm
B3 | 40 mm thick fine dressed stone flooring over 20 mm (average) thick base of cement mortar 1:5 (1 cement : 5 coarse sand) with joints finished flush. White sand stone
Outer Loo
| Location 1 |  | 6.907 | 0.55 |  | 3.7989 | sqm
| Location 2 |  | 9.46 | 0.55 |  | 5.203 | sqm
| Location 3 |  | 6.907 | 0.55 |  | 3.7989 | sqm
| Location 4 |  | 9.46 | 0.55 |  | 5.203 | sqm
| At different location as per structure demand |  |  |  |  | 2 | sqm
| Total |  |  |  |  | 20.0037 | sqm
B4 | Providing and laying in position cement concrete of specified grade excluding the cost of centering and shuttering - All work up to plinth level : 1:2:4 (1 cement : 2 coarse sand (zone-III) derived from natural sources : 4 graded stone aggregate 20 mm nominal size derived from natural sources)
Outer Loo
For drain
| 1) |  | 11.16 | 0.965 | 0.1 | 1.0769 | cum
| 2) |  | 6.91 | 0.965 | 0.1 | 0.66682 | cum
| 3) |  | 11.16 | 0.965 | 0.1 | 1.0769 | cum
| 4) |  | 6.91 | 0.965 | 0.1 | 0.66682 | cum
| Outer Loo |  | 4.96 | 8.61 | 0.1 | 4.2706 | cum
Staircase
| 1) |  | 6.245 | 1.708 | 0.1 | 1.0666 | cum
| 2) |  | 5.095 | 1.708 | 0.1 | 0.87023 | cum
| 3) |  | 1.64 | 1.708 | 0.1 | 0.28011 | cum
| 4) | 22 | 0.15 | 1.708 | 0.1 | 0.56364 | cum
Honoria Court
| Toilet Block | 2 | 2.12 | 4.02 | 0.1 | 1.7045 | cum
| Drying Area | 2 | 1.715 | 2.78 | 0.1 | 0.95354 | cum
| Changing Room | 2 | 6.71 | 10.975 | 0.1 | 14.7285 | cum
OGD
| Lower Ground Floor |  | 5 | 4.64 | 0.1 | 2.32 | cum
Upper Ground Floor
| Bath |  | 3.46 | 2.81 | 0.1 | 0.97226 | cum
| Toilet |  | 3.28 | 3.31 | 0.1 | 1.0857 | cum
| Toilet |  | 2.61 | 1.485 | 1.1 | 4.2634 | cum
First Floor
| Bath |  | 3.46 | 2.81 | 0.1 | 0.97226 | cum
| Toilet |  | 3.28 | 3.31 | 0.1 | 1.0857 | cum
| Toilet | 2 | 2.23 | 1.14 | 0.1 | 0.50844 | cum
| At different location as per structure demand |  |  |  |  | 5.87 | cum
| Total |  |  |  |  | 45.0029 | cum
B5 | Brick work with common burnt clay F.P.S. (non modular) bricks of class designation 7.5 in foundation and plinth in: Cement mortar 1:4 (1 cement : 4 coarse sand)
Outer Loo
Brick work for drain
| 1) | 2 | 11.16 | 0.23 | 0.3 | 1.5401 | cum
| 2) | 2 | 6.91 | 0.23 | 0.3 | 0.95358 | cum
Brick work for Staircase
| 1) | 1 | 6.245 | 0.23 | 1.708 | 2.4533 | cum
| 2) | 1 | 5.095 | 0.23 | 1.708 | 2.0015 | cum
| 3) | 1 | 1.64 | 0.23 | 1.708 | 0.64426 | cum
Outer Loo
| Wall 1 | 1 | 6.12 | 0.23 | 2.5 | 3.519 | cum
| Wall 2 | 1 | 2.985 | 0.23 | 2.5 | 1.7164 | cum
| Wall 3 | 2 | 6.12 | 0.115 | 1.2 | 1.6891 | cum
Honoria Court
| Wall 1 | 2 | 8.375 | 0.23 | 2.6 | 10.0165 | cum
| Wall 2 | 2 | 1.05 | 0.23 | 3 | 1.449 | cum
| Wall 3 | 2 | 1.502 | 0.23 | 3 | 2.0728 | cum
| Wall 4 | 2 | 2.12 | 0.23 | 3 | 2.9256 | cum
| Wall 5 | 4 | 6.05 | 0.115 | 1.2 | 3.3396 | cum
Wall 6
OGD
Lower Ground Floor
| Wall 1 | 1 | 4.998 | 0.115 | 2.6 | 1.4944 | cum
Upper Ground Floor
| Wall 1 | 1 | 4.048 | 0.115 | 2.6 | 1.2104 | cum
First Floor
| Wall 1 | 1 | 4.05 | 0.115 | 2.6 | 1.2109 | cum
| Wall 2 | 1 | 0.99 | 0.115 | 2.6 | 0.29601 | cum
| At different location as per structure demand |  |  |  |  | 6.76 | cum
| Total |  |  |  |  | 45.2924 | cum
B6 | 12 mm cement plaster finished with a floating coat of neat cement of mix : 1:4 (1 cement: 4 fine sand)
Honoria Court
| Wall 1 | 2 | 6.71 | 1.1 |  | 14.762 | sqm
| Wall 2 | 2 | 10.975 | 1.1 |  | 24.145 | sqm
| Wall 3 | 2 | 6.67 | 1.1 |  | 14.674 | sqm
| Wall 4 | 2 | 6.43 | 1.1 |  | 14.146 | sqm
| Wall 5 | 2 | 3.16 | 1.1 |  | 6.952 | sqm
| Wall 6 | 2 | 3.62 | 3.4 |  | 24.616 | sqm
| Wall 7 | 2 | 2.32 | 3.4 |  | 15.776 | sqm
| Wall 8 | 2 | 4.25 | 1.1 |  | 9.35 | sqm
| Wall 9 | 2 | 2.12 | 1.1 |  | 4.664 | sqm
| Wall 10 | 2 | 2.16 | 3.4 |  | 14.688 | sqm
| Wall 11 | 2 | 2.12 | 3.4 |  | 14.416 | sqm
| Wall 12 | 2 | 2.16 | 3.4 |  | 14.688 | sqm
| Wall 13 | 2 | 0.535 | 3.4 |  | 3.638 | sqm
| Wall 14 | 4 | 4.25 | 1.1 |  | 18.7 | sqm
| Wall 15 | 2 | 8.344 | 1.1 |  | 18.3568 | sqm
| Wall 16 | 2 | 8.344 | 1.1 |  | 18.3568 | sqm
OGD
Lower Ground Floor
| Wall 1 |  | 4.6 | 0.7 |  | 3.22 | sqm
| Wall 2 |  | 5 | 0.7 |  | 3.5 | sqm
| Wall 3 |  | 4.6 | 0.7 |  | 3.22 | sqm
| Wall 4 |  | 5 | 0.7 |  | 3.5 | sqm
Upper Ground Floor
Bath
| Wall 1 |  | 4.11 | 0.7 |  | 2.877 | sqm
| Wall 2 |  | 3.305 | 0.7 |  | 2.3135 | sqm
| Wall 3 |  | 2.225 | 0.7 |  | 1.5575 | sqm
| Wall 4 |  | 3.785 | 0.7 |  | 2.6495 | sqm
Toilet
| Wall 1 |  | 3.305 | 0.7 |  | 2.3135 | sqm
| Wall 2 |  | 4.03 | 0.7 |  | 2.821 | sqm
| Wall 3 |  | 3.785 | 0.7 |  | 2.6495 | sqm
| Wall 4 |  | 2.27 | 0.7 |  | 1.589 | sqm
Toilet
| Wall 1 |  | 2.61 | 0.7 |  | 1.827 | sqm
| Wall 2 |  | 1.48 | 0.7 |  | 1.036 | sqm
| Wall 3 |  | 2.61 | 0.7 |  | 1.827 | sqm
| Wall 4 |  | 1.48 | 0.7 |  | 1.036 | sqm
First Floor
Bath
| Wall 1 |  | 4.11 | 0.7 |  | 2.877 | sqm
| Wall 2 |  | 3.305 | 0.7 |  | 2.3135 | sqm
| Wall 3 |  | 2.225 | 0.7 |  | 1.5575 | sqm
| Wall 4 |  | 3.785 | 0.7 |  | 2.6495 | sqm
Toilet
| Wall 1 |  | 3.305 | 0.7 |  | 2.3135 | sqm
| Wall 2 |  | 4.03 | 0.7 |  | 2.821 | sqm
| Wall 3 |  | 3.785 | 0.7 |  | 2.6495 | sqm
| Wall 4 |  | 2.27 | 0.7 |  | 1.589 | sqm
Toilet
| Wall 1 | 2 | 2.23 | 0.7 |  | 3.122 | sqm
| Wall 2 | 2 | 1.14 | 0.7 |  | 1.596 | sqm
| Wall 3 | 2 | 2.23 | 0.7 |  | 3.122 | sqm
| Wall 4 | 2 | 1.14 | 0.7 |  | 1.596 | sqm
| Total a |  |  |  |  | 298.0716 | sqm
Deductions
Honoria Court
| Door 1 | 2 | 1.28 | 2.65 |  | 6.784 | sqm
| Door 2 | 4 | 0.75 | 2.65 |  | 7.95 | sqm
| Door 3 | 6 | 0.75 | 0.35 |  | 1.575 | sqm
| Window 1 | 16 | 1.2 | 1.05 |  | 20.16 | sqm
| Window 2 | 2 | 1.2 | 0.47 |  | 1.128 | sqm
| Total b |  |  |  |  | 37.597 | sqm
| Total (a-b) |  |  |  |  | 260.4746 | sqm
| At different location as per structure demand |  |  |  |  | 9.53 | sqm
| Total |  |  |  |  | 270.0046 | sqm
B7 | Wall painting with premium acrylic emulsion paint of interior grade, having VOC (Volatile Organic Compound ) content less than 50 grams/ litre of approved brand and manufacture, including applying additional coats wherever required to achieve even shade and colour. Two coats
| At different location as per structure demand |  |  |  |  | 300 | sqm
B8 | Structural steel work in single section, fixed with or without connecting plate, including cutting, hoisting, fixing in position and applying a priming coat of approved steel primer all complete. Heavy weight grating made with equal leg angle frame of 40x40x5 and Shutter of 35x35x5 ms angle with Ms flat (30x5)mm at top . the spacing between ms flat is 50mm dimensions, total weight of cover and frame to be not less than 30 kg
Outer Loo
For drain
| 1) |  | 11.16 |  | 30 | 334.8 | kg
| 2) |  | 6.91 |  | 30 | 207.3 | kg
| 3) |  | 11.16 |  | 30 | 334.8 | kg
| 4) |  | 6.91 |  | 30 | 207.3 | kg
| At different location as per structure demand |  |  |  |  | 65.8 | kg
| Total |  |  |  |  | 1150 | kg
B9 | Providing and laying 4" x 4" Polycrete pavers of dark gray and medium gray shades (as per sample approved) over a prepared base in cement mortar 1:4 (1 part cement : 4 parts coarse sand), including preparation of base, leveling, laying in approved pattern, filling of joints with fine sand/cement slurry, compacting, and curing, complete as per drawing and direction of the Engineer-in-Charge.
Outer Loo
Staircase
| 1) |  | 6.245 | 1.708 |  | 10.6665 | sqm
| 2) |  | 5.095 | 1.708 |  | 8.7023 | sqm
| 3) |  | 1.64 | 1.708 |  | 2.8011 | sqm
| 4) | 22 | 0.15 | 1.708 |  | 5.6364 | sqm
| At different location as per structure demand |  |  |  |  | 2 | sqm
| Total |  |  |  |  | 29.8062 | sqm
B10 | Random rubble masonry with hard stone in superstructure above plinth level and upto floor five level, including leveling up with cement concrete 1:6:12 (1 cement : 6 coarse sand : 12 graded stone aggregate 20 mm nominal size) at window sills, ceiling level and the like. Cement mortar 1:6 (1 cement : 6 coarse sand)
| For retaining wall |  | 5.2 | 0.6 | 1.5 | 4.68 | cum
| At different location as per structure demand |  |  |  |  | 0.32 | cum
| Total |  |  |  |  | 5 | cum
B11 | Steel work in built up tubular (round, square or rectangular hollow tubes etc.) trusses etc., including cutting, hoisting, fixing in position and applying a priming coat of approved steel primer, including welding and bolted with special shaped washers etc. complete. Hot finished seamless type tubes
| At different location as per structure demand |  |  |  |  | 1000 | kg
| Total |  |  |  |  | 1000 | kg
B12 | Kota stone slab flooring over 20 mm (average) thick base laid over and jointed with grey cement slurry mixed with pigment to match the shade of the slab, including rubbing and polishing complete with base of cement mortar 1 : 4 (1 cement : 4 coarse sand) : 25 mm thick
Honoria Court
| Pantry |  | 2.12 | 2.93 |  | 6.2116 | sqm
| Passage |  | 2.32 | 1.625 |  | 3.77 | sqm
| At different location as per structure demand |  |  |  |  | 5.02 | sqm
| Total |  |  |  |  | 15.0016 | sqm
B13 | Kota stone slabs 20 mm thick in risers of steps, skirting, dado and pillars laid on 12 mm (average) thick cement mortar 1:3 (1 cement: 3 coarse sand) and jointed with grey cement slurry mixed with pigment to match the shade of the slabs, including rubbing and polishing complete.
Honoria Court
| Pantry |  | 2.12 | 2.93 |  | 6.2116 | sqm
| Passage |  | 2.32 | 1.625 |  | 3.77 | sqm
| At different location as per structure demand |  |  |  |  | 5.02 | sqm
| Total |  |  |  |  | 15.0016 | sqm
B14 | Providing and laying Ceramic glazed floor tiles of size 300x300 mm(thickness to be specified by the manufacturer) of 1st quality conforming to IS : 15622 of approved make in colours such as White, Ivory, Grey, Fume Red Brown, laid on 20 mm thick cement mortar 1:4 (1 Cement : 4 Coarse sand), Jointing with grey cement slurry @ 3.3 kg/sqm including pointing the joints with white cement and matching pigment etc., complete.
Outer Loo
| For Flooring |  | 4.96 | 8.61 |  | 42.7056 | sqm
For Wall
Outer Loo
| Wall 1 |  | 4.96 | 3.01 |  | 14.9296 | sqm
| Wall 2 |  | 8.61 | 2.4 |  | 20.664 | sqm
| Wall 3 |  | 4.96 | 3.01 |  | 14.9296 | sqm
| Wall 4 |  | 8.61 | 2.4 |  | 20.664 | sqm
| Wall 5 |  | 6.088 | 2.4 |  | 14.6112 | sqm
| Wall 6 |  | 6.088 | 2.4 |  | 14.6112 | sqm
| Wall 7 |  | 1.262 | 2.4 |  | 3.0288 | sqm
| Wall 8 |  | 1.262 | 2.4 |  | 3.0288 | sqm
| Wall 9 |  | 2.754 | 2.4 |  | 6.6096 | sqm
Honoria Court
For Flooring
| 1 | 2 | 2.12 | 4.02 |  | 17.0448 | sqm
| 2 | 2 | 1.715 | 2.78 |  | 9.5354 | sqm
| 3 | 2 | 6.71 | 10.975 |  | 147.2845 | sqm
For Wall
| Wall 1 | 2 | 6.71 | 2.3 |  | 30.866 | sqm
| Wall 2 | 2 | 10.975 | 2.3 |  | 50.485 | sqm
| Wall 3 | 2 | 6.67 | 2.3 |  | 30.682 | sqm
| Wall 4 | 2 | 6.43 | 2.3 |  | 29.578 | sqm
| Wall 5 | 2 | 3.16 | 2.3 |  | 14.536 | sqm
| Wall 8 | 2 | 4.25 | 2.3 |  | 19.55 | sqm
| Wall 9 | 2 | 2.12 | 2.3 |  | 9.752 | sqm
| Wall 10 | 4 | 4.25 | 2.3 |  | 39.1 | sqm
| Wall 11 | 2 | 8.344 | 2.3 |  | 38.3824 | sqm
| Wall 12 | 2 | 8.344 | 2.3 |  | 38.3824 | sqm
OGD
For Flooring
| Lower Ground Floor |  | 5 | 4.64 |  | 23.2 | sqm
Upper Ground Floor
| Bath |  | 3.46 | 2.81 |  | 9.7226 | sqm
| Toilet |  | 3.28 | 3.31 |  | 10.8568 | sqm
| Toilet |  | 2.61 | 1.5 |  | 3.915 | sqm
First Floor
| Bath |  | 3.46 | 2.81 |  | 9.7226 | sqm
| Toilet |  | 3.28 | 3.31 |  | 10.8568 | sqm
| Toilet |  | 2.61 | 1.5 |  | 3.915 | sqm
For Wall
Lower Ground Floor
| Wall 1 |  | 4.6 | 2.3 |  | 10.58 | sqm
| Wall 2 |  | 5 | 2.3 |  | 11.5 | sqm
| Wall 3 |  | 4.6 | 2.3 |  | 10.58 | sqm
| Wall 4 |  | 5 | 2.3 |  | 11.5 | sqm
Upper Ground Floor
Bath
| Wall 1 |  | 4.11 | 2.3 |  | 9.453 | sqm
| Wall 2 |  | 3.305 | 2.3 |  | 7.6015 | sqm
| Wall 3 |  | 2.225 | 2.3 |  | 5.1175 | sqm
| Wall 4 |  | 3.785 | 2.3 |  | 8.7055 | sqm
Toilet
| Wall 1 |  | 3.305 | 2.3 |  | 7.6015 | sqm
| Wall 2 |  | 4.03 | 2.3 |  | 9.269 | sqm
| Wall 3 |  | 3.785 | 2.3 |  | 8.7055 | sqm
| Wall 4 |  | 2.27 | 2.3 |  | 5.221 | sqm
Toilet
| Wall 1 |  | 2.61 | 2.3 |  | 6.003 | sqm
| Wall 2 |  | 1.48 | 2.3 |  | 3.404 | sqm
| Wall 3 |  | 2.61 | 2.3 |  | 6.003 | sqm
| Wall 4 |  | 1.48 | 2.3 |  | 3.404 | sqm
First Floor
Bath
| Wall 1 |  | 4.11 | 2.3 |  | 9.453 | sqm
| Wall 2 |  | 3.305 | 2.3 |  | 7.6015 | sqm
| Wall 3 |  | 2.225 | 2.3 |  | 5.1175 | sqm
| Wall 4 |  | 3.785 | 2.3 |  | 8.7055 | sqm
Toilet
| Wall 1 |  | 3.305 | 2.3 |  | 7.6015 | sqm
| Wall 2 |  | 4.03 | 2.3 |  | 9.269 | sqm
| Wall 3 |  | 3.785 | 2.3 |  | 8.7055 | sqm
| Wall 4 |  | 2.27 | 2.3 |  | 5.221 | sqm
Toilet
| Wall 1 | 2 | 2.23 | 2.3 |  | 10.258 | sqm
| Wall 2 | 2 | 1.14 | 2.3 |  | 5.244 | sqm
| Wall 3 | 2 | 2.23 | 2.3 |  | 10.258 | sqm
| Wall 4 | 2 | 1.14 | 2.3 |  | 5.244 | sqm
| Total a |  |  |  |  | 920.4767 | sqm
Deductions
Outer Loo
| Door 1 | 1 | 0.99 | 1.94 |  | 1.9206 | sqm
| Window 1 | 10 | 0.872 | 0.41 |  | 3.5752 | sqm
Honoria Court
| Door 1 | 6 | 0.75 | 2.3 |  | 10.35 | sqm
| Window 1 | 16 | 1.2 | 0.58 |  | 11.136 | sqm
OGD
| Door 1 | 1 | 1.05 | 2.1 |  | 2.205 | sqm
| Door 2 | 3 | 0.75 | 2.1 |  | 4.725 | sqm
| Door 3 | 4 | 0.75 | 2.1 |  | 6.3 | sqm
| Window 1 | 3 | 0.45 | 1.4 |  | 1.89 | sqm
| Ventilator 1 | 4 | 0.9 | 0.5 |  | 1.8 | sqm
| Ventilator 2 | 6 | 0.9 | 0.8 |  | 4.32 | sqm
| Ventilator 3 | 2 | 0.9 | 0.8 |  | 1.44 | sqm
| Total b |  |  |  |  | 49.6618 | sqm
| TOTAL(a-b) |  |  |  |  | 870.8149 | sqm
| At different location as per structure demand |  |  |  |  | 129.19 | sqm
| Total |  |  |  |  | 1000.0049 | sqm
B15 | Providing wood work in frames of doors, windows, clerestory windows and other frames, wrought framed and fixed in position with hold fast lugs or with dash fasteners of required dia & length (hold fast lugs or dash fastener shall be paid for separately). Sal wood
| At different location as per structure demand |  |  |  |  | 0.5 | cum
B16 | Providing and fixing panelled or panelled and glazed shutters for doors, windows and clerestory windows, fixing with butt hinges of required size with necessary screws, excluding panelling which will be paid for separately, all complete as per direction of Engineer-in-charge. (Note: Butt hinges and necessary screws shall be paid separately) Second class teak wood
| At different location as per structure demand |  |  |  |  | 30 | sqm
B17 | Providing and fixing panelling or panelling and glazing in panelled or panelled and glazed shutters for doors, windows and clerestory windows (Area of opening for panel inserts excluding portion inside grooves or rebates to be measured). Panelling for panelled or panelled and glazed shutters 25 mm to 40 mm thick.
a | Second class teak wood |  |  |  |  | 20 | sqm
b | Float glass panes-4 mm thick glass pane (weight not less than 10 kg/sqm). |  |  |  |  | 10 | sqm
B18 | Providing and fixing approved quality natural stone cladding of 18–25 mm thickness, in required sizes, shapes, and patterns, on walls, columns, or façade surfaces, as per drawings, specifications, and as directed by the Engineer-in-Charge.
| Wall 1 | 2 | 16.2 | 5.7 |  | 184.68 | sqm
| Wall 2 | 2 | 16.2 | 1.01 |  | 32.724 | sqm
| Wall 3 | 2 | 17 | 0.1 |  | 3.4 | sqm
| Wall 4 | 2 | 17 | 0.15 |  | 5.1 | sqm
| Wall 5 | 1 | 5.31 | 4.01 |  | 21.2931 | sqm
| Rear Column | 1 | 8.335 | 5.7 |  | 47.5095 | sqm
| Wall 6 | 16 | 0.716 |  |  | 11.456 | sqm
| Column | 14 | 2.56 | 0.15 |  | 5.376 | sqm
| Column | 1 | 3.905 | 0.15 |  | 0.58575 | sqm
| Parapet | 32 | 0.9 | 0.475 |  | 13.68 | sqm
| Parapet | 16 | 1.88 | 0.45 |  | 13.536 | sqm
| Window 1 | 22 | 6.1 | 0.1 |  | 13.42 | sqm
| Window 2 | 3 | 7.18 | 0.1 |  | 2.154 | sqm
| Window 3 | 1 | 5.16 | 0.1 |  | 0.516 | sqm
| Total a |  |  |  |  | 294.7066 | sqm
Deduction
| Window 1 | 22 | 1.18 | 1.89 |  | 49.0644 | sqm
| Window 2 | 3 | 1.7 | 1.89 |  | 9.639 | sqm
| Window 3 | 1 | 1.69 | 0.49 |  | 0.8281 | sqm
| Door 1 | 1 | 2.65 | 0.9 |  | 2.385 | sqm
| Door 2 | 1 | 1.69 | 0.9 |  | 1.521 | sqm
| Total b |  |  |  |  | 63.4375 | sqm
| Total(a+b) |  |  |  |  | 231.2691 | sqm
Cladding
| Arch | 16 | 1.24 |  |  | 19.84 | sqm
| At different location as per structure demand |  |  |  |  | 8.89 | sqm
| Total |  |  |  |  | 259.9991 | sqm
B19 | Brick work in plain arches in superstructure above plinth level and upto floor five level including centering and shuttering complete for span up to 6 metres with common burnt clay F.P.S. (non modular) bricks of class designation 7.5 in cement mortar 1:3 (1 cement : 3 coarse sand)
| For Archs in façade |  |  |  |  | 30 | cum
B20 | Brick work with common burnt clay F.P.S. (non modular) bricks of class designation 7.5 in foundation and plinth in: Cement mortar 1:4 (1 cement : 4 coarse sand)
| Parapet | 16 | 1.71 |  | 0.23 | 6.2928 | cum
| Planter | 14 | 1.53 | 0.42 | 0.23 | 2.0692 | cum
|  | 1 | 1.95 | 0.42 | 0.23 | 0.18837 | cum
|  | 1 | 3.6 | 0.42 | 0.23 | 0.34776 | cum
| At different location as per structure demand |  |  |  |  | 1.1 | cum
| Total |  |  |  |  | 9.9981 | cum
B21 | Providing and fixing factory made uPVC door frame made of uPVC extruded sections having an overall dimension as below (tolerance ±1mm), with wall thickness 2.0 mm (± 0.2 mm), corners of the door frame to be Jointed with galvanized brackets and stainless steel screws, joints mitred and Plastic welded. The hinge side vertical of the frames reinforced by galvanized M.S. tube of size 19 X 19 mm and 1 mm (± 0.1 mm) wall thickness and 3 nos. stainless steel hinges fixed to the frame complete as per manufacturer’s specification and direction of Engineerin- charge. Extruded section profile size 48x40 mm
Outer Loo
| 1 | 24 | 0.87 |  |  | 20.88 | rmt
| 2 | 24 | 0.41 |  |  | 9.84 | rmt
| At different location as per structure demand |  |  |  |  | 4.28 | rmt
| Total |  |  |  |  | 35 | rmt
B22 | 24 mm thick factory made PVC door shutters made of styles and rails of a uPVC hollow section of size 59x24 mm and wall thickness 2 mm (± 0.2 mm) with inbuilt edging on both sides. The styles and rails mitred and joint at the corners by means of M.S. galvanised/ plastic brackets of size 75x220 mm having wall thickness 1.0 mm and stainless steel screws. The styles of the shutter reinforced by inserting galvanised M.S. tube of size 20x20 mm and 1 mm (± 0.1mm) wall thickness. The lock rail made up of ‘H’ section, a uPVC hollow section of size 100x24 mm and 2 mm (± 0.2 mm) wall thickness, fixed to the shutter styles by means of plastic/galvanised M.S. ‘U’ cleats. The shutter frame filled with a uPVC multi-chambered single panel of size not less than 620 mm, having over all thickness of 20 mm and 1 mm (± 0.1 mm) wall thickness. The panels filled vertically and tie bar at two places by inserting horizontally 6 mm galvanised M.S. rod and fastened with nuts and washers, complete as per manufacturer’s specification and direction of Engineerin- charge. (For W.C. and bathroom door shutter).
| Outer Loo | 12 | 0.87 | 0.41 |  | 4.2804 | sqm
| At different location as per structure demand |  |  |  |  | 3.72 | sqm
| Total |  |  |  |  | 8.0004 | sqm
B23 | Providing & Fixing double skin full height 12 mm thick solid partition of make STYLAM or similar (upto the 7 feet), vertical members to be fixed on the SS plate and caping on the floor. Approved BWR ply as per IS:303, finished both side with approved 1 mm laminate surface complete with door shutter with laminate finish matching to the other available side of the partition, to be incorporated with necessary hinges, sliding bolt from inside, handle and all complete as per design, direction and approval of the Engineer.
Outer Loo
| 1 | 2 | 6.06 | 1.995 |  | 24.1794 | sqm
| 2 | 8 | 1.25 | 1.995 |  | 19.95 | sqm
Honoria Court
| 1 | 4 | 7.225 | 1.995 |  | 57.6555 | sqm
| 2 | 30 | 1.27 | 1.995 |  | 76.0095 | sqm
| 3 | 1 | 6.65 | 1.995 |  | 13.2668 | sqm
| 4 | 2 | 1.16 | 1.995 |  | 4.6284 | sqm
OGD
Lower Ground Floor
| 1 | 1 | 4.94 | 1.995 |  | 9.8553 | sqm
| 2 | 5 | 1.3 | 1.995 |  | 12.9675 | sqm
| 3 | 1 | 2.525 | 1.995 |  | 5.0374 | sqm
Upper Ground Floor
| 1 | 5 | 1.25 | 1.995 |  | 12.4688 | sqm
| 2 | 2 | 3.325 | 1.995 |  | 13.2668 | sqm
| First Floor | 2 | 1.16 | 1.995 |  | 4.6284 | sqm
| 1 | 5 | 1.25 | 1.995 |  | 12.4688 | sqm
| 2 | 2 | 3.325 | 1.995 |  | 13.2668 | sqm
| At different location as per structure demand |  |  |  |  | 10.35 | sqm
| Total |  |  |  |  | 289.9991 | sqm
B24 | Providing and fixing false ceiling at all heights including providing and fixing of frame work made of special sections, power pressed from M.S. sheets and galvanized with zinc coating of 120 gms/sqm (both side inclusive) as per IS : 277 and consisting of angle cleats of size 25 mm wide x 1.6 mm thick with flanges of 27 mm and 37mm, at 1200 mm centre to centre, one flange fixed to the ceiling with dash fastener 12.5 mm dia x 50 mm long with 6 mm dia bolts, other flange of cleat fixed to the angle hangers of 25x10x0.50 mm of required length with nuts & bolts of required size and other end of angle hanger fixed with intermediate G.I. channels 45x15x0.9 mm running at the spacing of 1200 mm centre to centre, to which the ceiling section 0.5 mm thick bottom wedge of 80 mm with tapered flanges of 26 mm each having lips of 10.5 mm, at 450 mm centre to centre, shall be fixed in a direction perpendicular to G.I. intermediate channel with connecting clips made out of 2.64 mm dia x 230 mm long G.I. wire at every junction, including fixing perimeter channels 0.5 mm thick 27 mm high having flanges of 20 mm and 30 mm long, the perimeter of ceiling fixed to wall/partition with the help of rawl plugs at 450 mm centre, with 25 mm long dry wall screws @ 230 mm interval, including fixing of gypsum board to ceiling section and perimeter channel with the help of dry wall screws of size 3.5 x 25 mm at 230 mm c/c, including jointing and finishing to a flush finish of tapered and square edges of the board with recommended jointing compound , jointing tapes , finishing with jointing compound in 3 layers covering upto 150 mm on both sides of joint and two coats of primer suitable for board, all as per manufacturer’s specification and also including the cost of making openings for light fittings, grills, diffusers, cutouts made with frame of perimeter channels suitably fixed, all complete as per drawings, specification and direction of the Engineer in Charge but excluding the cost of painting with :
| Outer Loo | 1 | 4.945 | 8.6 |  | 42.527 | sqm
Honoria Court
| Toilet Block | 2 | 6.71 | 10.975 |  | 147.2845 | sqm
| Drying Area | 2 | 1.72 | 2.78 |  | 9.5632 | sqm
| Changing Room | 2 | 2.12 | 4.02 |  | 17.0448 | sqm
| Pantry | 2 | 2.12 | 2.93 |  | 12.4232 | sqm
| Passage | 2 | 2.32 | 1.625 |  | 7.54 | sqm
OGD
| Lower Ground Floor | 1 | 5 | 4.64 |  | 23.2 | sqm
Upper Ground Floor
| Bath | 1 | 3.46 | 2.81 |  | 9.7226 | sqm
| Toilet | 1 | 3.28 | 3.31 |  | 10.8568 | sqm
| Lobby | 1 | 5 | 2.375 |  | 11.875 | sqm
First Floor
| Bath | 1 | 3.46 | 2.81 |  | 9.7226 | sqm
| Toilet | 1 | 3.28 | 3.31 |  | 10.8568 | sqm
| Lobby | 1 | 5 | 2.375 |  | 11.875 | sqm
| Toilet | 2 | 2.19 | 1.14 |  | 4.9932 | sqm
| At different location as per structure demand |  |  |  |  | 10.52 | sqm
| Total |  |  |  |  | 340.0047 | sqm
C. Roofing works
C1 | Provide and fixing 19 mm thick marine plywood (water-resistant) onto rafters using suitable screws and washers, including all required fixing materials (nails, screws, washers, adhesives), aligning, leveling, cutting to fit at joints, and finishing. Work to be done complete, as per Engineer‑in‑Charge approval.
| For Old GD roof sheet area |  |  |  |  | 300 | sqm
| Total |  |  |  |  | 300 | sqm
C2 | Providng and fixing insulated PUFF sheet Roofing with the following specificifications -Panel Specifications: Roof shall be made of sandwich panel, made out of 0.50mm colour coated galvalume steel sheets spec 150gsm & 550mpa as as outer & inner cladding will be 0.40 mm colour coated galvalume sheet sheet spec 150 gsm & 550 mpa on both side of PUFF. Make of the sheet to be OEM TATA/JSW PRIME material. . The total thickness of panel will be 50/80 mm for roof, panel PU foam will be CFC free , self-extinguishing, Fire resistance type having density of 40 kg/cum. The Panel are joined together by tongue & groove method, complete in all respect including all the accessories. Fixing Mechanism: The sheeting will be fixed using galvanized self-drilling, self-tapping fasteners with EPDM seals to ensure secure attachment and weatherproofing.
| For Old GD roof sheet area |  |  |  |  | 420 | sqm
| Total |  |  |  |  | 420 | sqm
C3 | Providing and fixing flashings, Cappings, valleys manufactured same material as mentioned for roof sheets above in standard lengths of 2.5 mtr. And fixed by means of hex-head self-drilling stitching screws. 501 to 1000 mm Girth in Ridges, flashings, aprons, barge boards (Make of the sheet to be OEM TATA/JSW PRIME material)
| Outer Loo | 3 | 10.66 |  |  | 31.98 | rmt
External Roof Canopy
| Roof 1 | 1 | 22.67 |  |  | 22.67 | rmt
| Roof 2 | 1 | 6.641 |  |  | 6.641 | rmt
| Roof 3 | 1 | 7.305 |  |  | 7.305 | rmt
| Roof 4 | 1 | 54.44 |  |  | 54.44 | rmt
| Roof 5 | 1 | 10.61 |  |  | 10.61 | rmt
| Roof 6 | 1 | 6.553 |  |  | 6.553 | rmt
| Roof 7 | 1 | 13.062 |  |  | 13.062 | rmt
| Roof 8 | 1 | 8.207 |  |  | 8.207 | rmt
| At different location as per structure demand |  |  |  |  | 8.53 | rmt
| Total |  |  |  |  | 169.998 | rmt
C4 | Providing and Fixing Gutters manufactured same material as mentioned for roof sheets without PUFF insultation above in standard lengths of 2.5 mtr. And fixed by means of hex-head self-drilling stitching screws. 501 to 1000 mm Girth (Make of the sheet to be OEM TATA/JSW PRIME material)
| Outer Loo | 2 | 10.66 |  |  | 21.32 | rmt
External Roof Canopy
| Roof 1 | 2 | 22.67 |  |  | 45.34 | rmt
| Roof 2 | 1 | 6.641 |  |  | 6.641 | rmt
| Roof 4 | 1 | 4.669 |  |  | 4.669 | rmt
| Roof 5 | 2 | 2.899 |  |  | 5.798 | rmt
| Roof 6 | 2 | 6.553 |  |  | 13.106 | rmt
| Roof 7 | 2 | 13.062 |  |  | 26.124 | rmt
| Roof 8 | 2 | 7.6 |  |  | 15.2 | rmt
| At different location as per structure demand |  |  |  |  | 6.8 | rmt
| Total |  |  |  |  | 144.998 | rmt
C5 | Providing and fixing precoated galvanised iron profile sheets (size, shape and pitch of corrugation as approved by Engineer-in-Charge) of total coated thickness 0.50 mm (base metal of minimum 0.45 mm thickness with total coating thickness of 0.05mm) with zinc coating 120 grams per sqm as per IS: 277, in 240 mpa steel grade, 5-7 microns epoxy primer onboth side of the sheet and polyester top coat 15-18 microns. Sheet should have protective guard film of 25 microns minimum to avoid scratches during transportation and should be supplied in single length upto 12 metre or as desired by Engineer-in-charge. The sheet shall be fixed using self drilling /self tapping screws of size (5.5x 55 mm) with EPDM seal, complete upto any pitch in horizontal/ vertical or curved surfaces, excluding the cost of purlins, rafters and trusses and including cutting to size and shape wherever required.
| Outer Loo |  |  |  |  | 80.82 | sqm
External Roof Canopy
| Roof 1 |  |  |  |  | 64.383 | sqm
| Roof 2 |  |  |  |  | 12.72 | sqm
| Roof 3 |  |  |  |  | 10.69 | sqm
| Roof 4 |  |  |  |  | 69.346 | sqm
| Roof 5 |  |  |  |  | 14.22 | sqm
| Roof 6 |  |  |  |  | 19.149 | sqm
| Roof 7 |  |  |  |  | 29.99 | sqm
| Roof 8 |  |  |  |  | 22.51 | sqm
| Roof 9 |  |  |  |  | 6.27 | sqm
| At different location as per structure demand |  |  |  |  | 9.9 | sqm
| Total |  |  |  |  | 339.998 | sqm
C6 | Providing and fixing precoated galvanised steel sheet roofing accessories of total coated thickness 0.50 mm (base metal of minimum 0.45 mm thickness with total coating thickness of 0.05 mm) with Zinc coating 120 gram per sqm as per IS: 277, in 240 mpa steel grade, 5-7 microns epoxy primer on both side of the sheet and polyester top coat 15-18 microns using self drilling/ self tapping screws complete : Flashings/ Aprons.( Upto 600 mm)
| Outer Loo |  |  |  |  | 80.82 | sqm
External Roof Canopy
| Roof 1 |  |  |  |  | 64.383 | sqm
| Roof 2 |  |  |  |  | 12.72 | sqm
| Roof 3 |  |  |  |  | 10.69 | sqm
| Roof 4 |  |  |  |  | 69.346 | sqm
| Roof 5 |  |  |  |  | 14.22 | sqm
| Roof 6 |  |  |  |  | 19.149 | sqm
| Roof 7 |  |  |  |  | 29.99 | sqm
| Roof 8 |  |  |  |  | 22.51 | sqm
| Roof 9 |  |  |  |  | 6.27 | sqm
| At different location as per structure demand |  |  |  |  | 9.9 | sqm
| Total |  |  |  |  | 339.998 | sqm
C7 | Structural steel work riveted, bolted or welded in built up sections, trusses and framed work, including cutting, hoisting, fixing in position and applying a priming coat of approved steel primer all complete.
Roof 1
| Column (50x50mm) | 20 | 2.31 |  | 4.4 | 203.28 | kg
| Rafter (50x50mm) | 10 | 2.64 |  | 4.4 | 116.16 | kg
| Purlin (50x50mm) | 7 | 22.67 |  | 4.4 | 698.236 | kg
Roof 2
| Column (35x35mm) | 16 | 2.71 |  | 4.4 | 190.784 | kg
| Beam (35x35mm) | 12 | 3.8
| Rafter (50x50mm) | 19 | 2.388 |  | 4.4 | 199.6368 | kg
| Purlin (50x50mm) | 10 | 3.152 |  | 4.4 | 138.688 | kg
Roof 3
| Column (40x40mm) | 5 | 2.2 |  | 4.4 | 48.4 | kg
| Rafter (50x50mm) | 5 | 1.48 |  | 4.4 | 32.56 | kg
| Purlin (50x50mm) | 2 | 7.303 |  | 4.4 | 64.2664 | kg
Roof 4
| Bracket (50x50MM) | 16 | 4.067 |  | 4.4 | 286.3168 | kg
| Purlin (50x50mm) | 3 | 55.66 |  | 4.4 | 734.712 | kg
Roof 5
| Column (35x35mm) | 16 | 2.94 |  | 4.4 | 206.976 | kg
| Beam (35x35mm) | 16 | 2.39 |  | 4.4 | 168.256 | kg
| Rafter (50x50mm) | 20 | 1.729 |  | 4.4 | 152.152 | kg
| Purlin (50x50mm) | 12 | 2.91 |  | 4.4 | 153.648 | kg
Roof 6
| Column (50x50mm) | 8 | 3.08 |  | 4.4 | 108.416 | kg
| Rafter (50x50mm) | 5 | 2.74 |  | 4.4 | 60.28 | kg
| Purlin (50x50mm) | 7 | 6.55 |  | 4.4 | 201.74 | kg
Roof 7
| Column (50x50mm) | 22 | 2.311 |  | 4.4 | 223.7048 | kg
| Rafter (50x50mm) | 11 | 2.266 |  | 4.4 | 109.6744 | kg
| Purlin (50x50mm) | 5 | 13.06 |  | 4.4 | 287.32 | kg
Roof 8
| Column (50x50mm) | 6 | 2.91 |  | 4.4 | 76.824 | kg
| Rafter (50x50mm) | 4 | 2.87 |  | 4.4 | 50.512 | kg
| Purlin (50x50mm) | 7 | 7.6 |  | 4.4 | 234.08 | kg
Roof 9
| Bracket (50x50MM) | 24 | 2.71 |  | 4.4 | 286.176 | kg
| At different location as per structure demand |  |  |  |  | 23.38 | kg
| Total |  |  |  |  | 5056.1792 | kg
D. Plumbing & Sanitary works
D1 | Providing and fixing white vitreous china extended wall mounting water closet of size 780x370x690 mm of approved shape including providing & fixing white vitreous china cistern with dual flush fitting, of flushing capacity 3 litre/ 6 litre (adjustable to 4 litre/ 8 litres), including seat cover, and cistern fittings, nuts, bolts and gasket etc complete.
| Outer Loo | 10 |  |  |  | 10
| Honoria Court | 20 |  |  |  | 20
| OGD | 12 |  |  |  | 12
| Total |  |  |  |  | 42
D2 | Providing and fixing wash basin with C.I. brackets, 15 mm C.P. brass pillar taps, 32 mm C.P. brass waste of standard pattern, including painting of fittings and brackets, cutting and making good the walls wherever require: White Vitreous China Flat back wash basin size 450x 300 mm with single 15 mm C.P. brass pillar tap
| Outer Loo | 7 |  |  |  | 7
| Honoria Court | 34 |  |  |  | 34
| OGD | 18 |  |  |  | 18
| Total |  |  |  |  | 59
D3 | Providing and fixing CP Brass 32 mm size Bottle Trap of approved quality & make and as per the direction of Engineer-in-charge.
| Outer Loo | 7 |  |  |  | 7
| Honoria Court | 34 |  |  |  | 34
| OGD | 18 |  |  |  | 18
| Total |  |  |  |  | 59
D4 | Providing and fixing toilet paper holder : C.P. brass
| Outer Loo | 10 |  |  |  | 10
| Honoria Court | 20 |  |  |  | 20
| OGD | 12 |  |  |  | 12
| Total |  |  |  |  | 42
D5 | Providing and fixing Health faucet with 1 metre long Flexible tube and C.P. wall hook with PVC & SS Screws wherever required make and as per the direction of Engineer-in-charge.
| Outer Loo | 10 |  |  |  | 10
| Honoria Court | 20 |  |  |  | 20
| OGD | 12 |  |  |  | 12
| Total |  |  |  |  | 42
D6 | Providing and fixing of C.P. Soap dish complete as per instruction of Engineer-in-charge.
| Outer Loo | 4 |  |  |  | 4
| Honoria Court | 14 |  |  |  | 14
| OGD | 13 |  |  |  | 13
| Total |  |  |  |  | 31
D7 | Providing and fixing C.P Towel Rail 600mm long fixed to PVC cleats with C.p brass screws including cutting and making good the walls wherever required.
| Honoria Court | 10 |  |  |  | 10
| OGD | 9 |  |  |  | 9
| Total |  |  |  |  | 19
D8 | Providing and fixing C.P Single lever concealed diverter and Bath spout for bath and shower with Button at Top complete as per direction of the Engineer-in-charge
| Honoria Court | 10 |  |  |  | 10
| OGD | 9 |  |  |  | 9
| Total |  |  |  |  | 10
D9 | Providing and Fixing Shower Head Over head rose shower with revoling joint ( with boday roation) & 115 mm long shower arm complete as directed by enginner in charge
| Honoria Court | 10 |  |  |  | 10
| OGD | 9 |  |  |  | 9
Total
10
D10 | Providing and fixing C.P. brass long body bib cock of approved quality conforming to IS standards and weighing not less than 690 gms.15 mm nominal bore
| Outer Loo | 10 |  |  |  | 10
| Honoria Court | 20 |  |  |  | 20
| OGD | 12 |  |  |  | 12
| Total |  |  |  |  | 42
D11 | Providing and fixing C.P. brass stop cock (concealed) of standard design and of approved make conforming to IS:8931. 15 mm nominal bore
| Outer Loo | 14 |  |  |  | 14
| Honoria Court | 65 |  |  |  | 65
| OGD | 36 |  |  |  | 36
| Total |  |  |  |  | 115
D12 | Providing and fixing C.P. brass angle valve for basin mixer and geyser points of approved quality conforming to IS:8931 15 mm nominal bore
| Outer Loo | 14 |  |  |  | 14
| Honoria Court | 65 |  |  |  | 65
| OGD | 36 |  |  |  | 36
| Total |  |  |  |  | 115
D13 | Providing and fixing of C.P towel ring square/circular fixed to wooden cleats with C.P brass screws including cutting and making good the walls wherever required.
| Outer Loo | 4 |  |  |  | 4
| Honoria Court | 14 |  |  |  | 14
| OGD | 13 |  |  |  | 13
| Total |  |  |  |  | 31
D14 | Providing and fixing Chlorinated Polyvinyl Chloride (CPVC) pipes, having thermal stability for hot & cold water supply, including all CPVC plain & brass threaded fittings and fixing the pipe with clamps at 1.00 m spacing. This includes jointing of pipes & fittings with one step CPVC solvent cement and the cost of cutting chases and making good the same including testing of joints complete as per direction of Engineer in Charge. Concealed work, including cutting chases and making good the walls etc.
| 15 mm nominal dia Pipes |  |  |  |  | 100 | metre
| 20 mm nominal dia Pipes |  |  |  |  | 80 | metre
| 25 mm nominal dia Pipes |  |  |  |  | 80 | metre
| 32 mm nominal dia Pipes |  |  |  |  | 70 | metre
D15 | Providing and fixing Chlorinated Polyvinyl Chloride (CPVC) pipes, having thermal stability for hot & cold water supply including all CPVC plain & brass threaded fittings This includes jointing of pipes & fittings with one step CPVC solvent cement, trenching, refilling & testing of joints complete as per direction of Engineer in Charge. External work
| 15 mm nominal dia Pipes |  |  |  |  | 150 | metre
| 20 mm nominal dia Pipes |  |  |  |  | 120 | metre
| 25 mm nominal dia Pipes |  |  |  |  | 60 | metre
| 32 mm nominal dia Pipes |  |  |  |  | 50 | metre
D16 | Providing and laying Non Pressure NP-3 class (Medium duty) R.C.C. pipes including collars/spigot jointed with stiff mixture of cement mortar in the proportion of 1:2 (1 cement : 2 fine sand) including testing of jointsetc. Complete 450 mm dia RCC pipes.
| For drains |  |  |  |  | 20 | rmt
E17 | Constructing brick masonry manhole in cement mortar 1:4 ( 1 cement : 4 coarse sand ) with R.C.C. top slab with 1:1.5:3 mix (1 cement : 1.5 coarse sand (zone-III) : 3 graded stone aggregate 20 mm nominal size), foundation concrete 1:4:8 mix (1 cement : 4 coarse sand (zone-III) : 8 graded stone aggregate 40 mm nominal size), inside plastering 12 mm thick with cement mortar 1:3 (1 cement : 3 coarse sand) finished with floating coat of neat cement and making channels in cement concrete 1:2:4 (1 cement : 2 coarse sand : 4 graded stone aggregate 20 mm nominal size) finished with a floating coat of neat cement complete as per standard design : Inside size 90x80 cm and 45 cm deep including C.I. cover with frame (light duty) 455x610 mm internal dimensions, total weight of cover and frame to be not less than 38 kg (weight of cover 23 kg and weight of frame 15 kg) : With common burnt clay F.P.S. (non modular) bricks of class designation 7.5
| For drain and plinth protection |  |  |  |  | 2 | each
E.Electrical Work
E1 | Supply, Wiring, Testing & Commissioning for switch board controlled light points with 3 X 1.5sq.mm FRLS PVC insulated copper wire and earthing with 1.5 sq.mm. FRLS PVC insulated copper wire in insurface / recessed Medium class FRLS PVC conduit, surface tee, saddles,conduit fixing material, MS Connector, including providing & fixing of modular switches as specified complete with modular plate with GI boxes of suitable as complete as required.
E1.1 | First Point (One point controlled by one no. 6 amps switch.) (Normal Light Point)
| Outer Loo |  |  |  |  | 10 | nos.
| Honoria Court |  |  |  |  | 20 | nos.
| OLD GD Holding House |  |  |  |  | 24 | nos.
| Total |  |  |  |  | 54 | nos.
E1.2 | same as the above for Looping Point
| Outer Loo |  |  |  |  | 47 | nos.
| Honoria Court |  |  |  |  | 44 | nos.
| OLD GD Holding House |  |  |  |  | 33 | nos.
| Total |  |  |  |  | 124 | nos.
E2 | Supply, Wiring, Testing & Commissioning for MCB controlled light points with 2 x 2.5 + 1 X 1.5 sq.mm FRLS PVC insulated copper wires in recessed / surface mounted in in insurface / recessed Medium class FRLS PVC conduit, surface tee, saddles, conduit fixing material, MS Connector, along with all required fittings. (Cost of MCB not to be included)
E2.1 | First Point (First light points controlled by one no.6A SP MCB)
| Outer Loo |  |  |  |  | 3 | nos.
| Honoria Court |  |  |  |  | 5 | nos.
| OLD GD Holding House |  |  |  |  | 6 | nos.
| Total |  |  |  |  | 14 | nos.
E2.2 | same as the above for Looping Point
| Outer Loo |  |  |  |  | 10 | nos.
| Honoria Court |  |  |  |  | 5 | nos.
| OLD GD Holding House |  |  |  |  | 6 | nos.
| Total |  |  |  |  | 21 | nos.
E3 | Supply, Wiring, Testing & Commissioning for 6 A multistandard shutterd switched socket outlet with 3 x 1.5 sq mm FRLS PVC insulated copper wire & earthing with 1.5 sq.mm FRLS PVC insulated copper wire in surface / recessed Medium class FRLS PVC conduit, surface tee, saddles,conduit fixing material, MS Connector, including providing & fixing of 6amps modular switch, socket complete with modular plate with suitable size of GI box complete in all respect.
| Outer Loo |  |  |  |  | 2 | nos.
| Honoria Court |  |  |  |  | 7 | nos.
| OLD GD Holding House |  |  |  |  | 8 | nos.
| Total |  |  |  |  | 17 | nos.
E4 | Supply, Wiring, Testing & Commissioning for 1 nos, 16 A shuttered, switched socket outlets with 2 x4 +1 x 2.5 sq.mm FRLS PVC insulated copper wire & earthing with 2.5 sq.mm FRLS PVC insulated copper wire in surface / recessed Medium class FRLS PVC conduit, including providing & fixing of 1 nos. of 16amps modular switched socket outlets alongwith 1nos 16 A switch with modular plate with GI box complete.
| Outer Loo |  |  |  |  | 2 | nos.
| Honoria Court |  |  |  |  | 6 | nos.
| OLD GD Holding House |  |  |  |  | 7 | nos.
| Total |  |  |  |  | 15 | nos.
E5 | Supply and wiring of exhaust fan point with 3 X 1.5 sq.mm FRLS PVC insulated copper conductor cable in in surface / recessed GI conduit, fixing on surface or wall/ceiling including fixing of saddles etc. including galvanised M.S. box, modular range of plate switches, 6A socket, modular cover plate, PVC insulated copper earth wire etc. complete as required.
| Outer Loo |  |  |  |  | 12 | nos.
| Honoria Court |  |  |  |  | 6 | nos.
| OLD GD Holding House |  |  |  |  | 18 | nos.
| Total |  |  |  |  | 36 | nos.
E6 | Providing and fixing in position the following FRLS PVC conduits including all accessories concealed in F. ceiling (PVC conduit not to be instaUed above false ceilfng) /waif/ floor as required including M.S. junction or pull boxes with 3mm thick perspex sheet cover plate compl-ete with 1.6 mm dia G.I. pull wires in the length of conduit.
E6.1 | 20 mm dia conduit ( 1.6 mm thick) |  |  |  |  | 100 | rmt
E6.2 | 25 mm dia conduit (1.6 mm thick) |  |  |  |  | 250 | rmt
E6.3 | 32 mm dia conduit (2.0 mm thick) |  |  |  |  | 200 | rmt
E8 | Supply & Installation, Testing & Commissioning of 250 mm dia exhaust fan with all accessories as complete as required. (Make -Havells / Oriant / Bajaj ).
| Outer Loo |  |  |  |  | 12 | nos.
| Honoria Court |  |  |  |  | 6 | nos.
| OLD GD Holding House |  |  |  |  | 18 | nos.
| Total |  |  |  |  | 36 | nos.
E9 | Supplying of light fixtures as per sample approved. | [5 empty] | L.S